DUKE x LENOVO (2026-2027)

Week Of 13th Sep-19th Sep

This week focused on brainstorming and interpreting the data after completing our initial exploratory data analysis (EDA). We presented our business requirements-gathering analysis and discussed different pricing strategies, optimization objectives, and the overall project scope.

Work Completed

- Presented our business requirements-gathering analysis.

- Discussed the project’s primary objective and potential pricing strategies.

- Identified best-selling enterprise products as the initial focus for the MVP because this segment has the strongest data availability.

- Agreed that profit maximization will be the initial primary objective, while revenue, margin, and units sold may be included but at a different weightage.

- Discussed using a weighted decision matrix to balance competing business objectives.

- Identified price tiers as guardrails to keep pricing recommendations realistic.

- Submitted the team norms assignment.

- Began background research on pricing strategies used in e-commerce, including dynamic pricing, competitive pricing, value-based pricing, promotional pricing, and product-level pricing.

Proposed Recommendations

The initial stage plans on developing an initial pricing recommendation tool for selected best-selling enterprise products. The tool will use relevant product and sales data to generate pricing recommendations within defined price-tier guardrails.

The dashboard may allow stakeholders to enter/view different decision scenarios, for eg-

- Select a specific product or product group.

- Review recommended prices.

- Compare potential outcomes related to profit, revenue, margin, and units sold.

- Adjust the relative importance, or weight, of different business objectives.

- Understand the reasoning behind the recommended price.

The first phase will focus on developing a practical MVP for a selected group of products rather than creating models for all products in the dataset.

Work in Progress

- Developing the detailed business scope document.

- Creating a mock-up of the pricing recommendation dashboard.

- Conducting research on industry and e-commerce pricing strategies.

- Finalizing the optimization objective and weighting approach.

- Identifying the most relevant products and data fields for the MVP.

- Defining the model constraints and price-tier guardrails.

Roadblocks and Open Questions

- The team is still finalizing whether profit should be the main optimization objective or whether revenue, margin, and units sold should also be optimized at a same weight.

- There are trade-offs between the different objectives. For example, a price that increases revenue may not necessarily maximize profit or units sold.

- The dataset contains approximately 2,200 unique products, so the initial product sample still needs to be narrowed.

- Some fields, including tax and sales channel information, contain missing values or may add complexity to the model.

- The team needs further clarification on how state-specific tax differences should be handled if we include tax.

- We also need to understand how pricing recommendations for one product may affect the sales of other products in the portfolio.

- Client feedback is needed to validate the proposed business scope, pricing objectives, and dashboard functionality.

Next Steps

Next week, we plan to complete the first version of the business scope document, continue refining the dashboard mock-up, finalize the initial product sample, and further develop the pricing strategy and optimization approach. We will also use client feedback to confirm the project direction and prepare the materials for the next review.